## Project_Info
TIO2 SPRINT INTELLIGENCE · PROJECT INFORMATION
Project Name | Sponsor | Business Unit | Project Manager | Start Date | Target End Date | Sprint Length (Days) | Methodology | Customer | Status
TIO2 – Telematics Gateway ECU Modernization | Dr. Klaus Bergmann | Commercial Vehicles | Suresh Iyer | 2025-01-20 | 2025-05-11 | 14 | Agile Scrum | Daimler Truck | Active
KEY PROJECT METRICS
Total Sprints | 8
Sprint Length (days) | 14
Target Confidence Level | 80%
Current Sprint | 4
Sprints Completed | 3
Sprints Remaining | 5
Total Team Size | 8
Technology Domain | Automotive Embedded Software
Compliance Target | MISRA C:2012, ASPICE L2
Release Cadence | 45-Day Delivery Cycle

## Team
TIO2 – TEAM RESOURCE REGISTER
Resource Name | Role | Primary Skill | Secondary Skill | Skill Level | Allocation % | Availability % | Notes
Karthik Subramaniam | Technical Lead / AUTOSAR Architect | AUTOSAR Stack Configuration | MCAL Driver Integration | Expert | 100% | 100% | Lead for BSW baseline, RTE generation, OS scheduling. Acts as architecture reviewer for all AUTOSAR modules.
Priya Meenakshi | Senior CAN / Protocols Engineer | CAN / J1939 Protocol Development | COM Stack & Signal Mapping | Advanced | 100% | 100% | Owns J1939 stack, CAN frame routing, address claiming, COM PDU configuration. CANoe scripting.
Arjun Sundaram | Diagnostics Engineer | UDS Diagnostics & DTC Management | DCM / DEM Module Configuration | Advanced | 100% | 80% | Owns all UDS services (0x10–0x2E), DTC management, DCM/DEM config. 80% availability; 20% on parallel ASPICE audit task.
Vikram Narayanan | System Architect / Integration Lead | ECU Integration & Gateway Routing | PDU Configuration | Expert | 100% | 100% | Owns gateway routing tables, PDU config, end-to-end ECU integration, fleet telemetry pipeline design.
Akshaya Krishnan | Test Engineer | HIL Testing & CANoe Automation | Regression & Integration Testing | Advanced | 100% | 100% | Owns CANoe test harness, HIL bench execution, regression suites, OTA cycle validation. Test vehicle TV-07 dependency.
Sandeep Annamalai | Cybersecurity Engineer | Automotive Cybersecurity (EVITA) | SecOC & Secure Boot | Advanced | 80% | 80% | Owns SecOC, HSM integration, TLS 1.3, IDS, secure boot chain. 80% allocated; 20% on corporate security audit. HSM board blocked (BLK-003).
Divya Rajalakshmi | Scrum Master | Agile Delivery & Sprint Tracking | Stakeholder Communication | Expert | 100% | 100% | Owns sprint ceremonies, velocity tracking, stakeholder reporting, risk escalation, Definition of Done governance.
Meena Balasubramanian | OTA / Firmware Engineer | OTA Firmware Update Mechanisms | Manifest & Delta Packaging | Intermediate | 100% | 100% | Owns OTA session manager, delta packaging, rollback logic, progress reporting. Backend API contract blocked (BLK-004).

## Sprint_Plan
TIO2 – SPRINT PLAN
Sprint Name | Start Date | End Date | Duration (Days) | Sprint Goal | Status | Velocity (h) | Carry-Over Items
Sprint 1 | 2025-01-20 | 2025-02-02 | 14 | Platform Setup: Establish development environment, toolchain configuration (ETAS ISOLAR-A/B), AUTOSAR BSW baseline (MICROSAR), CAN driver scaffolding, ECU hardware abstraction layer init. | Completed | 340 | 1
Sprint 2 | 2025-02-03 | 2025-02-16 | 14 | CAN Communication: Implement J1939 stack, CAN frame routing logic, signal mapping, PDU configuration, gateway routing table, CANoe test harness, address claiming procedure. | Completed | 335 | 1
Sprint 3 | 2025-02-17 | 2025-03-02 | 14 | Diagnostics: Develop UDS services (0x10, 0x11, 0x14, 0x19, 0x22, 0x27, 0x2E), DTC management, diagnostic session control. OEM spec blocker caused rework (+50h overrun). | Completed | 410 | 4
Sprint 4 | 2025-03-03 | 2025-03-16 | 14 | AUTOSAR Integration: RTE generation, SWC port mapping, MCAL integration (SPI/LIN/Eth), DCM/DEM modules, COM stack signal routing, NvM, BSP validation. HW bench blocker active. | In Progress | 395 | 3
Sprint 5 | 2025-03-17 | 2025-03-30 | 14 | Cybersecurity: SecOC module, HSM key management & certificate provisioning, TLS 1.3 for backend, EVITA HSM driver, secure boot chain, IDS configuration. Contingent on BLK-003 resolution by Sprint 5 start. | Not Started | TBD | 0
Sprint 6 | 2025-03-31 | 2025-04-13 | 14 | OTA Updates: Firmware delta packaging, OTA session manager, rollback & recovery logic, manifest validation & signature verification, HIL OTA update cycle test. Blocked on backend API contract (BLK-004) — must resolve by Sprint 5 close. | Not Started | TBD | 0
Sprint 7 | 2025-04-14 | 2025-04-27 | 14 | System Integration: End-to-end ECU integration on HIL bench (TV-07 required), gateway routing validation, CAN+UDS+OTA regression suite, vehicle telemetry signal validation on target hardware. | Not Started | TBD | 0
Sprint 8 | 2025-04-28 | 2025-05-11 | 14 | Release Readiness: Final regression, FOTA end-to-end validation, MISRA C:2012 compliance review & waivers documentation, ASPICE L2 documentation package, customer sign-off with Daimler Truck engineering team. | Not Started | TBD | 0
VELOCITY SUMMARY (Completed Sprints)
Average Velocity (h/sprint) | 370
Velocity Std Dev (h) | 38.0789
Velocity CoV (%) — Monte Carlo Input | 10.29%

## Work_Items
TIO2 – WORK ITEM REGISTER (Sprint Backlog & Actuals)
Task ID | Task Name | Type | Sprint | Orig. Sprint | Owner | Required Skill | Priority | Orig Est (h) | Curr Est (h) | Actual Hrs | Remaining Hrs | Progress % | Status | Scope Change | Scope Reason
WI-001 | AUTOSAR BSW Baseline Configuration | Feature | Sprint 1 | Sprint 1 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 40 | 48 | 50 | 0 | 100% | Completed | Yes | Technical Debt – MICROSAR OS version mismatch required re-baselining
WI-002 | Development Toolchain Setup (ETAS ISOLAR-A/B) | Task | Sprint 1 | Sprint 1 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 16 | 17 | 0 | 100% | Completed | No
WI-003 | CAN Driver Scaffolding | Story | Sprint 1 | Sprint 1 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 24 | 28 | 30 | 0 | 100% | Completed | No
WI-004 | ECU Hardware Abstraction Layer (MCAL Init) | Feature | Sprint 1 | Sprint 1 | Karthik Subramaniam | MCAL Driver Integration | High | 32 | 36 | 38 | 0 | 100% | Completed | Yes | Customer Request – MCU variant changed from TC387 to TC397 after kickoff
WI-005 | CANoe Test Environment Setup | Task | Sprint 1 | Sprint 1 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 12 | 12 | 14 | 0 | 100% | Completed | No
WI-006 | AUTOSAR OS Task Scheduling Configuration | Story | Sprint 1 | Sprint 1 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 20 | 24 | 26 | 0 | 100% | Completed | Yes | Technical Debt – OS category reconfigured from BCC1 to ECC2 after load analysis
WI-007 | Spike: Evaluate ETAS RTA-OS vs MICROSAR OS | Spike | Sprint 1 | Sprint 1 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 16 | 18 | 0 | 100% | Completed | No
WI-008 | COM Stack Initial Configuration | Story | Sprint 1 | Sprint 1 | Priya Meenakshi | COM Stack & Signal Mapping | Medium | 16 | 20 | 22 | 0 | 100% | Completed | No
WI-009 | Version Control & CI Pipeline Setup | Task | Sprint 1 | Sprint 1 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | Medium | 12 | 12 | 13 | 0 | 100% | Completed | No | ⚠ DELIBERATE SKILL MISMATCH: CI setup by Cybersecurity engineer – see Team sheet note
WI-010 | Sprint 1 Definition of Done Review | Task | Sprint 1 | Sprint 1 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 9 | 0 | 100% | Completed | No
WI-011 | J1939 Protocol Stack Integration | Feature | Sprint 2 | Sprint 2 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 40 | 48 | 52 | 0 | 100% | Completed | Yes | Customer Request – Daimler requested NMEA 2000 bridge support; J1939 scope extended
WI-012 | CAN Frame Routing Logic Implementation | Feature | Sprint 2 | Sprint 2 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 32 | 38 | 40 | 0 | 100% | Completed | Yes | Technical Debt – Redundant routing paths added for gateway failover; scope +6h
WI-013 | Signal Mapping & PDU Configuration | Story | Sprint 2 | Sprint 2 | Vikram Narayanan | PDU Configuration | High | 24 | 24 | 26 | 0 | 100% | Completed | No
WI-014 | CAN Gateway Routing Table Configuration | Story | Sprint 2 | Sprint 2 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 20 | 26 | 28 | 0 | 100% | Completed | Yes | Customer Request – 12 additional routing rules added for OBD2 PGN filtering
WI-015 | CANoe Automated Test Harness (CAN Layer) | Task | Sprint 2 | Sprint 2 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 20 | 20 | 22 | 0 | 100% | Completed | No
WI-016 | Spike: CAN FD Feasibility for High-BW Signals | Spike | Sprint 2 | Sprint 2 | Vikram Narayanan | ECU Integration & Gateway Routing | Medium | 12 | 12 | 13 | 0 | 100% | Completed | No
WI-017 | CAN Bus Error Handling & Fault Injection Tests | Story | Sprint 2 | Sprint 2 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 16 | 20 | 21 | 0 | 100% | Completed | No
WI-018 | J1939 Address Claiming Procedure | Story | Sprint 2 | Sprint 2 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 16 | 16 | 17 | 0 | 100% | Completed | No
WI-019 | UDS Service 0x10 – Diagnostic Session Control | Feature | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 24 | 28 | 30 | 0 | 100% | Completed | No
WI-020 | UDS Service 0x27 – Security Access | Feature | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 20 | 24 | 26 | 0 | 100% | Completed | No
WI-021 | UDS Service 0x19 – Read DTC Information | Feature | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 24 | 30 | 32 | 0 | 100% | Completed | Yes | Customer Request – Daimler extended DTC snapshot data record size from 4 to 16 bytes
WI-022 | DTC Management – Fault Storage & Ageing | Story | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 20 | 24 | 24 | 0 | 100% | Completed | No
WI-023 | UDS Service 0x22/0x2E – Data Identifier R/W | Story | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 16 | 20 | 21 | 0 | 100% | Completed | No
WI-024 | Diagnostic Logging Module | Story | Sprint 3 | Sprint 3 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 16 | 16 | 18 | 0 | 100% | Completed | No
WI-025 | CANoe Diagnostic Test Script (KWP/UDS) | Task | Sprint 3 | Sprint 3 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 16 | 20 | 22 | 0 | 100% | Completed | No
WI-026 | Defect: UDS 0x10 Session Timeout Not Honoured | Defect | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 8 | 8 | 9 | 0 | 100% | Completed | No
WI-027 | Spike: OEM-Specific DTC Extension Requirements | Spike | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | Medium | 12 | 16 | 16 | 0 | 100% | Completed | No
WI-028 | Fleet Telemetry Data Pipeline Design | Feature | Sprint 4 | Sprint 3 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 24 | 32 | 20 | 12 | 62.5% | In Progress | Yes | Regulatory – GDPR data residency requirements added; pipeline design scope expanded mid-Sprint 3. Carried to Sprint 4.
WI-029 | AUTOSAR RTE Generation & SWC Port Mapping | Feature | Sprint 4 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 40 | 48 | 50 | 0 | 100% | Completed | No
WI-030 | MCAL Driver Integration (SPI, LIN, Ethernet) | Feature | Sprint 4 | Sprint 4 | Karthik Subramaniam | MCAL Driver Integration | High | 32 | 40 | 42 | 0 | 100% | Completed | Yes | Enhancement – Ethernet AUTOSAR Driver (EthIf/EthTrcv) added for OTA channel requirement
WI-031 | DCM Module Configuration & Session Handling | Story | Sprint 4 | Sprint 4 | Arjun Sundaram | DCM / DEM Module Configuration | High | 20 | 24 | 25 | 0 | 100% | Completed | No
WI-032 | DEM Module Configuration & Event Handling | Story | Sprint 4 | Sprint 4 | Arjun Sundaram | DCM / DEM Module Configuration | High | 20 | 24 | 24 | 0 | 100% | Completed | No
WI-033 | COM Stack Signal Routing (AUTOSAR COM) | Story | Sprint 4 | Sprint 4 | Priya Meenakshi | COM Stack & Signal Mapping | High | 24 | 28 | 30 | 0 | 100% | Completed | No
WI-034 | NvM Module – Non-Volatile Storage Configuration | Story | Sprint 4 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 16 | 20 | 21 | 0 | 100% | Completed | No
WI-035 | AUTOSAR Integration Test – RTE Scheduler | Task | Sprint 4 | Sprint 4 | Akshaya Krishnan | HIL Testing & CANoe Automation | High | 20 | 20 | 24 | 0 | 100% | Completed | No
WI-036 | Defect: RTE Runnable Period Drift Under Load | Defect | Sprint 4 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 12 | 12 | 14 | 0 | 100% | Completed | No
WI-037 | Gateway ECU Board Support Package Validation | Feature | Sprint 4 | Sprint 4 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 28 | 36 | 30 | 6 | 83.33% | In Progress | Yes | Enhancement – Additional board variants (VCU-A, VCU-B) added to validation scope. HW bench unavailable (BLK-002).
WI-038 | Memory Footprint Analysis & Stack Profiling | Task | Sprint 4 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 12 | 16 | 10 | 6 | 62.5% | In Progress | No | Carry-over from Sprint 4. Stack profiling blocked until BLK-002 hardware bench available.
WI-039 | Spike: AUTOSAR Adaptive vs Classic for OTA Path | Spike | Sprint 4 | Sprint 4 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 20 | 20 | 0 | 100% | Completed | No
WI-040 | Defect: COM PDU Transmission Timing Deviation | Defect | Sprint 5 | Sprint 4 | Priya Meenakshi | COM Stack & Signal Mapping | High | 10 | 10 | 0 | 10 | 0% | Blocked | No | Carried from Sprint 4. Root cause requires HW bench HB-03 for timing measurement. Blocked by BLK-002.
WI-041 | SecOC Module Implementation | Feature | Sprint 5 | Sprint 5 | Sandeep Annamalai | SecOC & Secure Boot | High | 40 | 44 | 0 | 44 | 0% | Not Started | No
WI-042 | HSM Key Management & Certificate Provisioning | Feature | Sprint 5 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | High | 36 | 36 | 0 | 36 | 0% | Not Started | No
WI-043 | Secure Boot Chain Verification | Story | Sprint 5 | Sprint 5 | Sandeep Annamalai | SecOC & Secure Boot | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-044 | TLS 1.3 for Backend Communication | Story | Sprint 5 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | High | 28 | 32 | 0 | 32 | 0% | Not Started | No
WI-045 | Cybersecurity Test Plan & Attack Surface Analysis | Task | Sprint 5 | Sprint 5 | Akshaya Krishnan | HIL Testing & CANoe Automation | High | 20 | 20 | 0 | 20 | 0% | Not Started | No | Blocked by BLK-003 – HSM board not available; test execution cannot begin
WI-046 | EVITA HSM Driver Integration | Story | Sprint 5 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | High | 20 | 24 | 0 | 24 | 0% | Not Started | No
WI-047 | Intrusion Detection System (IDS) Configuration | Story | Sprint 5 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | Medium | 16 | 20 | 0 | 20 | 0% | Not Started | No
WI-048 | OTA Session Manager Implementation | Feature | Sprint 6 | Sprint 6 | Meena Balasubramanian | OTA Firmware Update Mechanisms | High | 36 | 40 | 0 | 40 | 0% | Not Started | No | Backend API contract blocked (BLK-004). Target: contract by end of Sprint 5.
WI-049 | Firmware Delta Packaging Tool | Feature | Sprint 6 | Sprint 6 | Meena Balasubramanian | Manifest & Delta Packaging | High | 32 | 32 | 0 | 32 | 0% | Not Started | No
WI-050 | OTA Rollback & Recovery Logic | Story | Sprint 6 | Sprint 6 | Meena Balasubramanian | OTA Firmware Update Mechanisms | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-051 | Manifest Validation & Signature Verification | Story | Sprint 6 | Sprint 6 | Sandeep Annamalai | Manifest & Delta Packaging | High | 20 | 24 | 0 | 24 | 0% | Not Started | No
WI-052 | OTA Progress Reporting to Fleet Backend | Story | Sprint 6 | Sprint 6 | Meena Balasubramanian | OTA Firmware Update Mechanisms | Medium | 16 | 20 | 0 | 20 | 0% | Not Started | No
WI-053 | HIL Test: OTA Update Cycle Validation | Task | Sprint 6 | Sprint 6 | Akshaya Krishnan | HIL Testing & CANoe Automation | High | 20 | 20 | 0 | 20 | 0% | Not Started | No | Requires test vehicle TV-07 (BLK-005). Reconfirmed available Sprint 7.
WI-054 | Spike: Delta Compression Algorithm Evaluation | Spike | Sprint 6 | Sprint 6 | Meena Balasubramanian | Manifest & Delta Packaging | Medium | 16 | 16 | 0 | 16 | 0% | Not Started | No
WI-055 | End-to-End HIL Bench Integration Test | Feature | Sprint 7 | Sprint 7 | Akshaya Krishnan | HIL Testing & CANoe Automation | High | 48 | 56 | 0 | 56 | 0% | Not Started | No | Critical path. Requires BLK-005 resolved (TV-07 available). Buffer: 8h scope added per test manager.
WI-056 | Gateway Routing End-to-End Validation | Feature | Sprint 7 | Sprint 7 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 36 | 36 | 0 | 36 | 0% | Not Started | No
WI-057 | CAN + UDS + OTA Regression Test Suite | Task | Sprint 7 | Sprint 7 | Akshaya Krishnan | Regression & Integration Testing | High | 32 | 36 | 0 | 36 | 0% | Not Started | No
WI-058 | Vehicle Telemetry Signal Validation on Target | Story | Sprint 7 | Sprint 7 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-059 | Defect: CAN Timing Violation Under Full Bus Load | Defect | Sprint 7 | Sprint 7 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 12 | 16 | 0 | 16 | 0% | Not Started | No | Pre-emptively opened based on Sprint 4 COM PDU timing observations. Likely latent defect.
WI-060 | Final MISRA C:2012 Compliance Review & Waivers | Feature | Sprint 8 | Sprint 8 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 32 | 36 | 0 | 36 | 0% | Not Started | No
WI-061 | ASPICE L2 Audit Documentation Package | Feature | Sprint 8 | Sprint 8 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-062 | FOTA End-to-End System Validation | Feature | Sprint 8 | Sprint 8 | Meena Balasubramanian | OTA Firmware Update Mechanisms | High | 28 | 32 | 0 | 32 | 0% | Not Started | No
WI-063 | Customer Sign-Off Demo – Daimler Truck | Task | Sprint 8 | Sprint 8 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 16 | 0 | 16 | 0% | Not Started | No
WI-064 | Release Notes & Configuration Baseline Lock | Task | Sprint 8 | Sprint 8 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 12 | 12 | 0 | 12 | 0% | Not Started | No
WI-065 | Sprint 8 Definition of Done & Project Retrospective | Task | Sprint 8 | Sprint 8 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 0 | 8 | 0% | Not Started | No
TOTALS | [7 empty] | 1426 | 1628 | 964 | 722

## Dependencies
TIO2 – DEPENDENCY REGISTER (Critical Path & Lag Analysis)
Dep ID | Predecessor Task | Sucessor Task | Dependency Type | Critical Path | Lag Days | Notes
DEP-001 | WI-003 | WI-001 | Finish-To-Start | No | 0 | CAN Driver Scaffolding requires AUTOSAR BSW baseline fully configured
DEP-002 | WI-004 | WI-001 | Finish-To-Start | No | 0 | MCAL Init depends on BSW baseline OS and memory mapping
DEP-003 | WI-011 | WI-003 | Finish-To-Start | Yes | 0 | J1939 stack integration requires CAN driver scaffolding complete
DEP-004 | WI-013 | WI-003 | Finish-To-Start | No | 0 | PDU configuration builds on CAN driver and COM stack init
DEP-005 | WI-019 | WI-011 | Finish-To-Start | Yes | 0 | UDS diagnostic services require functional CAN/J1939 stack (transport layer)
DEP-006 | WI-024 | WI-022 | Finish-To-Start | No | 0 | Diagnostic Logging requires DTC management module operational
DEP-007 | WI-029 | WI-004 | Finish-To-Start | Yes | 0 | RTE generation depends on MCAL and BSW modules being integrated
DEP-008 | WI-031 | WI-019 | Finish-To-Start | No | 0 | DCM session handling depends on UDS Service 0x10 implementation
DEP-009 | WI-041 | WI-029 | Finish-To-Start | Yes | 1 | SecOC module requires RTE and COM stack integration complete. 1-day lag for RTE sign-off.
DEP-010 | WI-043 | WI-042 | Finish-To-Start | Yes | 2 | AUDIT FIX: Secure boot chain verification depends on HSM key management & certificate provisioning (was incorrectly DEP-010 WI-041). 2-day lag for HSM provisioning handoff.
DEP-011 | WI-048 | WI-043 | Finish-To-Start | Yes | 2 | OTA session manager requires secure channel (TLS/SecOC) established. 2-day lag for security sign-off.
DEP-012 | WI-051 | WI-048 | Finish-To-Start | No | 1 | Manifest validation depends on OTA session manager scaffolding. 1-day lag.
DEP-013 | WI-055 | WI-053 | Finish-To-Start | Yes | 1 | HIL bench integration requires OTA update cycle validation complete. 1-day lab setup lag.
DEP-014 | WI-060 | WI-055 | Finish-To-Start | Yes | 0 | Final MISRA C review requires system integration test sign-off
DEP-015 | WI-028 | WI-024 | Finish-To-Start | No | 0 | Fleet telemetry pipeline depends on Diagnostic Logging module
DEP-016 | WI-033 | WI-013 | Finish-To-Start | No | 0 | COM stack routing depends on signal mapping and PDU configuration
DEP-017 | WI-040 | WI-033 | Finish-To-Start | Yes | 0 | COM PDU timing defect investigation requires signal routing complete
DEP-018 | WI-056 | WI-048 | Finish-To-Start | No | 1 | Gateway routing E2E validation requires OTA session manager. 1-day integration lag.
DEP-019 | WI-049 | WI-054 | Finish-To-Start | No | 0 | Firmware Delta Packaging Tool implementation follows spike algorithm evaluation
DEP-020 | WI-057 | WI-055 | Finish-To-Start | No | 0 | Regression test suite runs after E2E HIL bench integration test passes
DEP-021 | WI-062 | WI-050 | Finish-To-Start | Yes | 1 | FOTA end-to-end validation requires rollback & recovery logic implemented. 1-day test prep lag.
DEP-022 | WI-044 | WI-042 | Finish-To-Start | No | 0 | TLS 1.3 backend communication depends on HSM key infrastructure from WI-042
DEP-023 | WI-058 | WI-056 | Finish-To-Start | No | 0 | Telemetry signal validation on target follows gateway routing E2E validation

## Blockers
TIO2 – BLOCKER REGISTER
Blocker ID | Related Task | Impacted Task IDs | Severity | Status | Owner | Raised Date | Target Resolution | Actual Resolution | Notes / Escalation Path
BLK-001 | WI-021 | WI-021, WI-027, WI-028 | Critical | Open | Arjun Sundaram | 2025-02-17 | 2025-03-14 | Open | OEM Diagnostic Specification DS_Diag_TIO2_v2.1 not released by Daimler Truck. Blocking UDS parameter tuning (snapshot record size, DTC extension byte layout) and fleet telemetry data schema. Escalated to Suresh Iyer → Dr. Klaus Bergmann on 2025-02-24. Partial spec received 2025-03-01 (sections 3–6 only). Sections 7–9 (DTC extensions) pending. IMPACT: 50h Sprint 3 overrun; WI-028 carried to Sprint 4.
BLK-002 | WI-037 | WI-030, WI-037, WI-038, WI-040 | High | Open | Vikram Narayanan | 2025-03-03 | 2025-03-17 | Open | Hardware Bench HB-03 allocated to calibration lab for ECU-B variant testing (parallel project). BSP validation, memory stack profiling, and COM PDU timing defect (WI-040) all require physical bench access for oscilloscope + CANalyzer timing measurements. Bench reconfirmed available 2025-03-18. IMPACT: 3 work items In Progress at Sprint 4 close; WI-040 blocked and rescheduled to Sprint 5.
BLK-003 | WI-041 | WI-041, WI-042, WI-043, WI-045, WI-046 | Critical | Open | Sandeep Annamalai | 2025-02-28 | 2025-03-20 | Open | NXP SE050 HSM evaluation board not received. PO raised 2025-02-10; NXP confirmed shipment delay due to semiconductor allocation issues. Expedited order placed 2025-02-28. Without HSM board: SecOC module cannot be validated, EVITA key provisioning cannot run, secure boot chain test cannot execute. Entire Sprint 5 Cybersecurity stream at risk. Mitigation: Procurement exploring alternate supplier (Infineon SLx9670). IMPACT: If not resolved by 2025-03-17 (Sprint 5 start), Sprint 5 scope must be rebalanced.
BLK-004 | WI-048 | WI-048, WI-050, WI-051, WI-052, WI-062 | High | Open | Meena Balasubramanian | 2025-03-03 | 2025-03-31 | Open | Daimler Fleet Team backend OTA API specification (REST contract + authentication schema) not delivered. Initial draft promised 2025-02-28; now delayed to end of March. OTA session manager, rollback logic, and fleet progress reporting cannot be finalised without the API contract. Manifest signature schema also depends on this. Escalated to Suresh Iyer 2025-03-05. IMPACT: OTA Sprint 6 stream at risk of 1-sprint slip.
BLK-005 | WI-053 | WI-053, WI-055, WI-057 | Medium | Open | Akshaya Krishnan | 2025-03-10 | 2025-04-07 | Open | Test Vehicle TV-07 (ECU integration bench target) allocated to parallel program (TIO1 winter testing) through end of Sprint 6. Confirmed available from 2025-04-14 (Sprint 7 start). HIL bench integration test and OTA cycle validation cannot start until vehicle is returned. IMPACT: Contained within Sprint 7 plan if TV-07 returned on schedule. Risk: if return delayed, Sprint 7 compression will threaten Sprint 8 release.

## Sprint_Actuals
TIO2 – SPRINT ACTUALS (Velocity History & Forecast Inputs)
Sprint | Planned Hours | Actual Hours | Variance (h) | Tasks Planned | Tasks Completed | Completion Rate | Carry-Over Count | Scope Change Hours | Blocker Impact (h) | Notes
Sprint 1 | 320 | 340 | 20 | 10 | 9 | 90% | 1 | 8 | 0 | Minor overrun. AUTOSAR BSW config more complex – MICROSAR OS category mismatch. CI pipeline on time. WI-006 OS scheduling carried 2h into Sprint 2 (overflow). Velocity baseline set: ~34h/person/sprint. BCC1→ECC2 OS reconfiguration added 6h unplanned.
Sprint 2 | 340 | 335 | -5 | 12 | 11 | 91.67% | 1 | 14 | 0 | Slightly under plan. J1939 address claiming completed 3h faster than estimated. CAN frame routing overran +6h (gateway redundancy scope, SC-005). WI-014 completed in overtime. WI-028 telemetry design started but not completed; flagged early carry risk.
Sprint 3 | 360 | 410 | 50 | 14 | 10 | 71.43% | 4 | 16 | 50 | Significant overrun (+50h). OEM diagnostic spec blocker (BLK-001) caused rework on UDS services 0x19 and 0x22 (DTC snapshot size change). Arjun availability reduced to 80% mid-sprint (ASPICE audit). 4 tasks carried: WI-028, WI-026 rework, plus 2 scope tasks.
Sprint 4 | 380 | 395 | 15 | 15 | 12 | 80% | 3 | 8 | 15 | Over by 15h. Hardware bench BLK-002 limited HIL validation time; Sneha could not complete bench-dependent tasks. 3 items remain In Progress: WI-037 (BSP), WI-038 (memory), WI-040 (COM PDU defect blocked). AUTOSAR RTE integration accepted by Daimler Truck.

## Lists (hidden)
ProjectStatus | SprintStatus | WorkItemType | Priority | WorkItemStatus | YesNo | ScopeReason | DependencyType | Severity | BlockerStatus | BlockerCategory | Owners | Skills | Sprints
Active | Not Started | Feature | Critical | Not Started | Yes | Customer Request | Finish-To-Start | Low | Open | Vendor | Karthik Subramaniam | AUTOSAR Stack Configuration | Sprint 1
On Hold | In Progress | Story | High | In Progress | No | Regulatory | Start-To-Start | Medium | In Progress | Hardware | Priya Meenakshi | MCAL Driver Integration | Sprint 2
Completed | Completed | Task | Medium | Blocked |  | Technical Debt | Finish-To-Finish | High | Resolved | Specification | Arjun Sundaram | CAN / J1939 Protocol Development | Sprint 3
Cancelled |  | Defect | Low | Completed |  | Defect |  | Critical | Closed | Resource | Vikram Narayanan | COM Stack & Signal Mapping | Sprint 4
|  | Spike |  | Deferred |  | Enhancement |  |  |  | Environment | Akshaya Krishnan | UDS Diagnostics & DTC Management | Sprint 5
[6 empty] | Other |  |  |  | Security | Sandeep Annamalai | DCM / DEM Module Configuration | Sprint 6
[10 empty] | Compliance | Divya Rajalakshmi | ECU Integration & Gateway Routing | Sprint 7
[11 empty] | Meena Balasubramanian | PDU Configuration | Sprint 8
[12 empty] | HIL Testing & CANoe Automation | VELOCITY SUMMARY (Completed Sprints)
[12 empty] | Regression & Integration Testing | Average Velocity (h/sprint)
[12 empty] | Automotive Cybersecurity (EVITA) | Velocity Std Dev (h)
[12 empty] | SecOC & Secure Boot | Velocity CoV (%) — Monte Carlo Input
Agile Delivery & Sprint Tracking
Stakeholder Communication
OTA Firmware Update Mechanisms
Manifest & Delta Packaging